## POA&M
SYNTHETIC SAMPLE – eMASS POA&M export layout (compatibility pending verification). Not real eMASS data.
POA&M ID | Control Acronym | CCI | Weakness Description | Source Identifying Weakness | Raw Severity | Residual Risk Level | Status | Scheduled Completion Date | Milestone with Completion Dates | POC | Resources Required | Comments
SYN-9001 | AC-2 | 000015 | SYNTHETIC: Inactive accounts are not disabled after 35 days | eMASS assessment | Moderate | Low | Ongoing | 06/30/2027 | 1) Configure automatic disable – 03/31/2027; 2) Verify – 06/30/2027 | Alex Rivera | 2 admin hours/week | SYNTHETIC sample
SYN-9002 | SI-2 |  | SYNTHETIC: Patch cadence exceeds 30 days for edge servers | ACAS | High | Moderate | Completed | 01/15/2027 | Patch and rescan
SYN-9003 | ZZ-9 |  | SYNTHETIC: control not in the system | Manual | Extreme |  | Ongoing | 13/45/2027